## Sheet1
Impact
Likelihood |  | Negligible | Acceptable | Major | Problematic | Catastrophic | Risks | Description | Response | Objective | Risk Code
| 75% - 100% | A1 | B1 | C1 | D1 | E1 | Power cut | Power loss to computer means the project can't be worked on | Keep a backup on a laptop | Make sure a computer is always available to use | D4
| 50% - 74% | A2 | B2 | C2 | D2 | E2 | Internet down | Internet down, no network communication | Use hotspot or use offline | Keep a system in place to continue working on the project even without internet | C4
| 25% - 49% | A3 | B3 | C3 | D3 | E3 | Time underestimated on certain aspects | Some aspects of the project require more time than initially calculated | Research topics and incorporate them quickly | Do extensive research into all technologies and dependencies required for the project | B2
| 0% - 24% | A4 | B4 | C4 | D4 | E4 | Hardware failure | Computer hardware failure, unable to use computer | Keep a backup on a working computer | Make sure all hardware on all computers is functional and maintained | E4
[7 empty] | Database/Codebase deletion or mass modification | Project files or records from database may be accidently deleted | Keep backups of all code files and databases | Daily backups of all changes of the day will ensure no major changes are lost | D2
[7 empty] | Strain Injuries | Working for too long may induce strain injuries | Keep moving throughout the day and take breaks | Make sure working position is confortable and regular breaks are taken | D3
[7 empty] | Complicated source code | The blueprint code is too complicated and needs greater understanding to build upon | Take longer to look through the project and understand its function | Make sure every aspect of the project is understood before starting | B2
[7 empty] | Features won't be completed in timeframe | Some features won't be completed in a week | Make a priority list of features, and implement them accordingly | Make sure enough time is allocated for the most important features | C2